## README
key | value
Dataset | Film Production Scene Readiness & Replan
Version | v4 — rebuilt for tool-call use, every table traces to every other table
Design goal | Every row in agent_results is derivable from the source tables below it (weather_readings, location_master, camera_schedule, stunt_safety_checklist, cast_availability). Nothing is a hardcoded answer with no data behind it.
Scenes covered | SC01, SC02, SC03, SC04, SC05, SC08, SC10, SC13 (8 scenes, one shoot date each)
Departments | weather, location, camera, stunt, cast (the 5 parallel agents)
Agent output schema | Every agent returns exactly this JSON shape for a given scene_id
department | one of: weather ¦ location ¦ camera ¦ stunt ¦ cast
status | one of: READY ¦ BLOCKED
ready_for_shooting | true only when status == READY
reason | empty string when READY; a one-sentence cause when BLOCKED
missing_items | semicolon-separated list of unmet checklist items; empty when READY
expected_items | semicolon-separated list of everything the department checks for this scene
metadata | a JSON string (parseable) with the raw values the decision was based on
Weather Agent reads | weather_requirements (thresholds) + weather_readings (forecast). INT scenes have no rows in either table -> agent returns READY, reason 'not applicable'.
Location Agent reads | location_master (permit_required, permit_status, operating_hours) joined to scene_master.location_id and shoot_time.
Camera Agent reads | scene_camera_plan (required camera_ids) joined to camera_schedule on (camera_id, shoot_date).
Stunt Agent reads | scene_stunt_plan (which stunt_id applies) + stunt_safety_checklist (per-item required/confirmed). No stunt_plan row -> agent returns READY, reason 'no stunt requirements'.
Cast Agent reads | scene_cast_map (who's needed) joined to cast_availability on (cast_id, shoot_date).
Replan Agent reads | production_state.blocking_department + issues_log + escalation_rules, to decide who the fix gets routed to.
Ready scenes (control cases) | SC01, SC02, SC04 — all five departments READY
Blocked scenes (one dept each) | SC03 (camera), SC05 (cast), SC08 (stunt), SC10 (location), SC13 (weather) — each blocked by exactly one department, every other department READY

## scene_master
scene_id | project_id | title | logline | int_ext | location_id | location_name | shoot_date | shoot_time | day_night | unit | scene_type
SC01 | FILM001 | Beach Meet & Car Arrival | Hero and heroine meet at sunset on a crowded beach as a car arrives. | EXT | MARINA_BEACH | Marina Beach | 2026-09-10 | 17:45 | SUNSET | MAIN | EMOTIONAL + ENTRY
SC02 | FILM001 | Apartment Introduction | Hero catches up with his best friend at his apartment before the trip. | INT | APARTMENT_SET | Apartment Set | 2026-09-11 | 14:00 | DAY | MAIN | DIALOGUE
SC03 | FILM001 | Boss Office Meeting | Hero is warned by his boss about the risk he is about to take. | INT | OFFICE_SET | Office Set | 2026-09-13 | 11:00 | DAY | MAIN | DIALOGUE
SC04 | FILM001 | Old City Street Chase | Hero chases a pickpocket through narrow market streets. | EXT | OLD_CITY_MARKET | Old City Market | 2026-09-12 | 15:00 | DAY | MAIN | ACTION CHASE
SC05 | FILM001 | Inspector Interrogation | Inspector Kumar questions Hero about the warehouse incident. | INT | INTERROGATION_ROOM_SET | Interrogation Room Set | 2026-09-14 | 10:00 | DAY | MAIN | DIALOGUE
SC08 | FILM001 | Warehouse Fight | Hero fights henchmen in an abandoned warehouse. | INT | ABANDONED_WAREHOUSE | Abandoned Warehouse | 2026-09-15 | 22:00 | NIGHT | MAIN | STUNT FIGHT
SC10 | FILM001 | Train Departure | Heroine leaves city on train while hero runs alongside. | EXT | CENTRAL_STATION | Central Station | 2026-09-16 | 14:00 | DAY | MAIN | EMOTIONAL DEPARTURE
SC13 | FILM001 | Rainy Street Goodbye | Hero and heroine say goodbye under controlled rain. | EXT | CITY_STREET_RAIN_RIG | City Street (Rain Rig) | 2026-09-18 | 19:00 | EVENING | MAIN | EMOTIONAL RAIN

## scene_breakdown
scene_id | primary_characters | extras_estimate | vehicles | key_props | action_beats | stunt_level | camera_style | weather_dependency | department_notes_camera | department_notes_stunt | department_notes_art
SC01 | Hero, Heroine, Villain | 50 | Car | Bag | Dialogue | NONE | Naturalistic coverage | Golden hour | Lens plan and camera count need DoP approval. | No stunt requirements for this scene. | Set dressing based on scene type and emotional tone.
SC02 | Hero, Friend | 0 |  | Photo album | Dialogue | NONE | Naturalistic coverage | Not applicable (INT) | Single-room dialogue coverage, minimal lighting setup. | No stunt requirements for this scene. | Lived-in apartment set dressing.
SC03 | Hero, Boss | 0 |  | Case file | Dialogue | NONE | Naturalistic coverage | Not applicable (INT) | Two-hander office dialogue, single camera setup. | No stunt requirements for this scene. | Corporate office set dressing.
SC04 | Hero, Pickpocket | 60 |  | Core hero props | Chase | MEDIUM | Handheld + Steadicam | Standard EXT weather | Lens plan and camera count need DoP approval. | Risk assessment required for stunt scenes. | Set dressing based on scene type and emotional tone.
SC05 | Hero, Inspector | 0 |  | Interrogation table, case file | Dialogue | NONE | Naturalistic coverage | Not applicable (INT) | Two-hander interrogation coverage, single camera setup. | No stunt requirements for this scene. | Police interrogation room set dressing.
SC08 | Hero, Henchmen | 20 |  | Core hero props | Fight | HIGH | Handheld + Steadicam | Not applicable (INT) | Lens plan and camera count need DoP approval. | Risk assessment required for stunt scenes. | Set dressing based on scene type and emotional tone.
SC10 | Hero, Heroine | 80 | Train | Core hero props | Chase | HIGH | Handheld + Steadicam | Standard EXT weather | Lens plan and camera count need DoP approval. | Risk assessment required for stunt scenes. | Set dressing based on scene type and emotional tone.
SC13 | Hero, Heroine | 30 |  | Umbrella | Dialogue | LOW | Naturalistic coverage | Controlled rain rig | Lens plan and camera count need DoP approval. | Risk assessment required for stunt scenes. | Set dressing based on scene type and emotional tone.

## location_master
location_id | location_name | location_type | city | permit_required | permit_status | operating_hours | noise_profile | access_constraints
MARINA_BEACH | Marina Beach | Beach | Chennai | TRUE | APPROVED | 06:00-22:00 | High | Crowd control
APARTMENT_SET | Apartment Set | Interior Set | Chennai | FALSE |  | 24x7 | Low | Standard crew access
OFFICE_SET | Office Set | Interior Set | Chennai | FALSE |  | 24x7 | Low | Standard crew access
OLD_CITY_MARKET | Old City Market | Market | Chennai | TRUE | APPROVED | 08:00-20:00 | High | Crowd control
INTERROGATION_ROOM_SET | Interrogation Room Set | Interior Set | Chennai | FALSE |  | 24x7 | Low | Standard crew access
ABANDONED_WAREHOUSE | Abandoned Warehouse | Interior Set | Chennai | FALSE |  | 24x7 | Medium | Standard crew access
CENTRAL_STATION | Central Station | Station | Chennai | TRUE | PENDING | 06:00-23:00 | High | Crowd control
CITY_STREET_RAIN_RIG | City Street (Rain Rig) | Street | Chennai | TRUE | APPROVED | 18:00-22:00 | High | Crowd control

## weather_requirements
scene_id | max_rain_probability | max_wind_kmh | notes
SC01 | 0.3 | 25 | Golden hour beach scene; moderate wind tolerance.
SC04 | 0.4 | 30 | Standard EXT chase; higher wind tolerance, handheld coverage.
SC10 | 0.4 | 35 | Open station platform; wind tolerance is high, rain is not.
SC13 | 0.3 | 20 | Controlled rain rig already active; real rain must stay low to protect continuity.

## weather_readings
scene_id | timestamp | location_id | rain_probability | wind_speed_kmh | visibility_km
SC01 | 2026-09-10 17:00 | MARINA_BEACH | 0.1 | 10 | 10
SC04 | 2026-09-12 14:00 | OLD_CITY_MARKET | 0.15 | 12 | 10
SC10 | 2026-09-16 13:00 | CENTRAL_STATION | 0.2 | 18 | 9
SC13 | 2026-09-18 18:00 | CITY_STREET_RAIN_RIG | 0.7 | 8 | 8

## camera_inventory
camera_id | label | type | model | owner_department | notes
CAM001 | Camera A | Digital Cinema | ARRI Alexa Mini | Camera | Primary A-camera for MAIN unit
CAM002 | Camera B | Digital Cinema | Sony FX9 | Camera | B-camera for coverage and handheld
CAM003 | Camera C | Digital Cinema | Blackmagic Pocket 6K | Camera | C-camera for inserts and montage
CAM004 | Drone 1 | Drone | DJI Inspire 3 | Camera | Drone shots for SC01 and SC10 only

## camera_schedule
camera_id | date | status | notes
CAM001 | 2026-09-10 | AVAILABLE
CAM002 | 2026-09-10 | AVAILABLE
CAM004 | 2026-09-10 | AVAILABLE
CAM001 | 2026-09-11 | AVAILABLE
CAM001 | 2026-09-12 | AVAILABLE
CAM003 | 2026-09-12 | AVAILABLE
CAM002 | 2026-09-13 | IN_MAINTENANCE | Sensor recalibration booked with vendor through end of day.
CAM001 | 2026-09-14 | AVAILABLE
CAM001 | 2026-09-15 | AVAILABLE
CAM002 | 2026-09-15 | AVAILABLE
CAM001 | 2026-09-16 | AVAILABLE
CAM002 | 2026-09-16 | AVAILABLE
CAM004 | 2026-09-16 | AVAILABLE
CAM001 | 2026-09-18 | AVAILABLE
CAM003 | 2026-09-18 | AVAILABLE

## scene_camera_plan
scene_id | camera_setup_id | camera_ids | notes
SC01 | CS01 | CAM001,CAM002,CAM004 | 3-camera + drone for beach meet and car arrival
SC02 | CS-SC02 | CAM001 | Single camera for apartment dialogue
SC03 | CS05 | CAM002 | Single camera for two-hander office dialogue
SC04 | CS02 | CAM001,CAM003 | Handheld + Steadicam for street chase
SC05 | CS-SC05 | CAM001 | Single camera for interrogation dialogue
SC08 | CS03 | CAM001,CAM002 | Multi-camera warehouse fight coverage
SC10 | CS06 | CAM001,CAM002,CAM004 | Multi-camera + drone for train platform chase
SC13 | CS04 | CAM001,CAM003 | Backlit rain emotional scene

## stunt_catalog
stunt_id | name | risk_level | description | requires_harness | requires_crash_mats | requires_medical
ST001 | Warehouse multi-opponent fight | HIGH | Hand-to-hand combat with falls from low platform and use of props. | TRUE | TRUE | TRUE
ST002 | Street foot chase | MEDIUM | Hero chases pickpocket through crowded market with obstacles. | FALSE | TRUE | TRUE
ST003 | Train departure run-along | HIGH | Hero runs alongside moving train on platform. | FALSE | TRUE | TRUE
ST004 | Night rain emotional scene safety | LOW | Controlled rain rig with slippery surfaces and umbrellas. | FALSE | FALSE | TRUE

## scene_stunt_plan
scene_id | stunt_id | stunt_plan_id | notes
SC04 | ST002 | SP01 | Old City street chase with obstacles and extras
SC08 | ST001 | SP02 | Warehouse fight with falls and weapon props
SC10 | ST003 | SP03 | Hero runs alongside train at station
SC13 | ST004 | SP04 | Rain rig safety, wet street conditions

## stunt_safety_checklist
checklist_id | scene_id | stunt_plan_id | item | required | confirmed | confirmed_by | notes
CHK01 | SC04 | SP01 | Crash mats | TRUE | TRUE | CR004
CHK02 | SC04 | SP01 | Medical support on set | TRUE | TRUE | CR004
CHK03 | SC08 | SP02 | Harness | TRUE | TRUE | CR004
CHK04 | SC08 | SP02 | Crash mats | TRUE | TRUE | CR004
CHK05 | SC08 | SP02 | Medical support on set | TRUE | FALSE |  | Set medic not yet assigned for the night shoot; required before a HIGH risk stunt can proceed.
CHK06 | SC10 | SP03 | Crash mats | TRUE | TRUE | CR004
CHK07 | SC10 | SP03 | Medical support on set | TRUE | TRUE | CR004
CHK08 | SC13 | SP04 | Medical support on set | TRUE | TRUE | CR004

## cast_directory
cast_id | name | role_name | gender | union_status | primary_contact
CAST001 | Arjun Rao | Hero | M | SAG | hero@example.com
CAST002 | Meera Nair | Heroine | F | SAG | heroine@example.com
CAST003 | Rahul Menon | Villain | M | SAG | villain@example.com
CAST004 | Anita Pillai | Friend | F | Non-union | friend@example.com
CAST005 | Sanjay Iyer | Boss | M | Non-union | boss@example.com
CAST006 | Inspector Kumar | Inspector | M | Non-union | inspector@example.com
CAST007 | Vikram Das | Pickpocket | M | Non-union | pickpocket@example.com

## cast_availability
cast_id | date | availability
CAST001 | 2026-09-10 | FULL_DAY
CAST001 | 2026-09-11 | FULL_DAY
CAST001 | 2026-09-12 | FULL_DAY
CAST001 | 2026-09-13 | FULL_DAY
CAST001 | 2026-09-14 | FULL_DAY
CAST001 | 2026-09-15 | FULL_DAY
CAST001 | 2026-09-16 | FULL_DAY
CAST001 | 2026-09-18 | FULL_DAY
CAST002 | 2026-09-10 | FULL_DAY
CAST002 | 2026-09-16 | FULL_DAY
CAST002 | 2026-09-18 | FULL_DAY
CAST003 | 2026-09-10 | FULL_DAY
CAST004 | 2026-09-11 | FULL_DAY
CAST005 | 2026-09-13 | FULL_DAY
CAST006 | 2026-09-14 | UNAVAILABLE
CAST007 | 2026-09-12 | FULL_DAY

## scene_cast_map
scene_id | cast_id | role_on_call_sheet
SC01 | CAST001 | Hero
SC01 | CAST002 | Heroine
SC01 | CAST003 | Villain
SC02 | CAST001 | Hero
SC02 | CAST004 | Friend
SC03 | CAST001 | Hero
SC03 | CAST005 | Boss
SC04 | CAST001 | Hero
SC04 | CAST007 | Pickpocket
SC05 | CAST001 | Hero
SC05 | CAST006 | Inspector
SC08 | CAST001 | Hero
SC10 | CAST001 | Hero
SC10 | CAST002 | Heroine
SC13 | CAST001 | Hero
SC13 | CAST002 | Heroine

## crew_directory
crew_id | name | role | department | email | shift
CR001 | Anand Rao | Assistant Director | Direction | ad@example.com | Day
CR002 | Priya Chandran | Line Producer | Production | lineproducer@example.com | Day
CR003 | Karthik Menon | Director of Photography | Camera | dop@example.com | Day
CR004 | Sara Thomas | Stunt Coordinator | Stunt | stunt@example.com | Day
CR005 | Divya Suresh | Location Manager | Locations | locations@example.com | Day
CR006 | Ravi Kannan | Casting Director | Casting | casting@example.com | Day

## schedule
schedule_id | scene_id | shoot_date | planned_start | planned_end | slot_order | location_id | status | notes
SCH001 | SC01 | 2026-09-10 | 17:45 | 18:30 | 1 | MARINA_BEACH | CONFIRMED | Golden hour
SCH002 | SC02 | 2026-09-11 | 14:00 | 15:00 | 2 | APARTMENT_SET | CONFIRMED | Interior dialogue
SCH003 | SC04 | 2026-09-12 | 15:00 | 16:30 | 3 | OLD_CITY_MARKET | CONFIRMED | Market crowd
SCH004 | SC03 | 2026-09-13 | 11:00 | 12:00 | 4 | OFFICE_SET | TENTATIVE | Pending B-camera availability
SCH005 | SC05 | 2026-09-14 | 10:00 | 11:00 | 5 | INTERROGATION_ROOM_SET | TENTATIVE | Pending inspector cast availability
SCH006 | SC08 | 2026-09-15 | 22:00 | 23:30 | 6 | ABANDONED_WAREHOUSE | TENTATIVE | Pending set medic assignment
SCH007 | SC10 | 2026-09-16 | 14:00 | 15:00 | 7 | CENTRAL_STATION | TENTATIVE | Pending station permit
SCH008 | SC13 | 2026-09-18 | 19:00 | 20:00 | 8 | CITY_STREET_RAIN_RIG | TENTATIVE | Pending weather clearance

## agent_results
scene_id | department | status | ready_for_shooting | reason | missing_items | expected_items | metadata
SC01 | weather | READY | TRUE |  |  | rain_probability<=0.3;wind_speed<=25kmh | {"rain_probability":0.1,"wind_speed_kmh":10,"threshold_rain":0.3}
SC01 | location | READY | TRUE |  |  | permit_status=APPROVED;within_operating_hours | {"location_id":"MARINA_BEACH","permit_status":"APPROVED","operating_hours":"06:00-22:00","shoot_time":"17:45"}
SC01 | camera | READY | TRUE |  |  | CAM001 available;CAM002 available;CAM004 available | {"camera_setup_id":"CS01","cameras":["CAM001","CAM002","CAM004"],"date":"2026-09-10"}
SC01 | stunt | READY | TRUE |  |  | no_stunt_required | {"stunt_level":"NONE"}
SC01 | cast | READY | TRUE |  |  | CAST001 available;CAST002 available;CAST003 available | {"date":"2026-09-10"}
SC02 | weather | READY | TRUE |  |  | not_applicable_interior_scene | {"int_ext":"INT"}
SC02 | location | READY | TRUE |  |  | permit_not_required;within_operating_hours | {"location_id":"APARTMENT_SET","permit_required":false}
SC02 | camera | READY | TRUE |  |  | CAM001 available | {"camera_setup_id":"CS-SC02","cameras":["CAM001"],"date":"2026-09-11"}
SC02 | stunt | READY | TRUE |  |  | no_stunt_required | {}
SC02 | cast | READY | TRUE |  |  | CAST001 available;CAST004 available | {"date":"2026-09-11"}
SC03 | weather | READY | TRUE |  |  | not_applicable_interior_scene | {"int_ext":"INT"}
SC03 | location | READY | TRUE |  |  | permit_not_required | {"location_id":"OFFICE_SET","permit_required":false}
SC03 | camera | BLOCKED | FALSE | Required camera CAM002 is in maintenance on the scheduled shoot date. | CAM002 available on 2026-09-13 | CAM002 available on 2026-09-13 | {"camera_setup_id":"CS05","cameras":["CAM002"],"camera_status":"IN_MAINTENANCE","date":"2026-09-13"}
SC03 | stunt | READY | TRUE |  |  | no_stunt_required | {}
SC03 | cast | READY | TRUE |  |  | CAST001 available;CAST005 available | {"date":"2026-09-13"}
SC04 | weather | READY | TRUE |  |  | rain_probability<=0.4;wind_speed<=30kmh | {"rain_probability":0.15,"wind_speed_kmh":12,"threshold_rain":0.4}
SC04 | location | READY | TRUE |  |  | permit_status=APPROVED | {"location_id":"OLD_CITY_MARKET","permit_status":"APPROVED"}
SC04 | camera | READY | TRUE |  |  | CAM001 available;CAM003 available | {"camera_setup_id":"CS02","cameras":["CAM001","CAM003"],"date":"2026-09-12"}
SC04 | stunt | READY | TRUE |  |  | crash_mats_confirmed;medical_support_confirmed | {"stunt_id":"ST002","risk_level":"MEDIUM"}
SC04 | cast | READY | TRUE |  |  | CAST001 available;CAST007 available | {"date":"2026-09-12"}
SC05 | weather | READY | TRUE |  |  | not_applicable_interior_scene | {"int_ext":"INT"}
SC05 | location | READY | TRUE |  |  | permit_not_required | {"location_id":"INTERROGATION_ROOM_SET","permit_required":false}
SC05 | camera | READY | TRUE |  |  | CAM001 available | {"camera_setup_id":"CS-SC05","cameras":["CAM001"],"date":"2026-09-14"}
SC05 | stunt | READY | TRUE |  |  | no_stunt_required | {}
SC05 | cast | BLOCKED | FALSE | Inspector Kumar (CAST006) is unavailable on the scheduled shoot date. | CAST006 available on 2026-09-14 | CAST001 available;CAST006 available | {"date":"2026-09-14","unavailable_cast":["CAST006"]}
SC08 | weather | READY | TRUE |  |  | not_applicable_interior_scene | {"int_ext":"INT"}
SC08 | location | READY | TRUE |  |  | permit_not_required | {"location_id":"ABANDONED_WAREHOUSE","permit_required":false}
SC08 | camera | READY | TRUE |  |  | CAM001 available;CAM002 available | {"camera_setup_id":"CS03","cameras":["CAM001","CAM002"],"date":"2026-09-15"}
SC08 | stunt | BLOCKED | FALSE | Medical support on set has not been confirmed for this HIGH risk stunt sequence. | Medical support on set confirmed | Harness confirmed;Crash mats confirmed;Medical support on set confirmed | {"stunt_id":"ST001","risk_level":"HIGH","stunt_plan_id":"SP02"}
SC08 | cast | READY | TRUE |  |  | CAST001 available | {"date":"2026-09-15"}
SC10 | weather | READY | TRUE |  |  | rain_probability<=0.4;wind_speed<=35kmh | {"rain_probability":0.2,"wind_speed_kmh":18,"threshold_rain":0.4}
SC10 | location | BLOCKED | FALSE | Central Station location permit is still PENDING approval. | Permit approved for CENTRAL_STATION | Permit approved for CENTRAL_STATION;within_operating_hours | {"location_id":"CENTRAL_STATION","permit_status":"PENDING"}
SC10 | camera | READY | TRUE |  |  | CAM001 available;CAM002 available;CAM004 available | {"camera_setup_id":"CS06","cameras":["CAM001","CAM002","CAM004"],"date":"2026-09-16"}
SC10 | stunt | READY | TRUE |  |  | crash_mats_confirmed;medical_support_confirmed | {"stunt_id":"ST003","risk_level":"HIGH"}
SC10 | cast | READY | TRUE |  |  | CAST001 available;CAST002 available | {"date":"2026-09-16"}
SC13 | weather | BLOCKED | FALSE | Forecast rain probability (70%) exceeds the safe threshold (30%) for the controlled rain rig; risk of real weather interfering with rig continuity. | rain_probability<=0.3 (actual 0.7) | rain_probability<=0.3;wind_speed<=20kmh | {"rain_probability":0.7,"wind_speed_kmh":8,"threshold_rain":0.3}
SC13 | location | READY | TRUE |  |  | permit_status=APPROVED | {"location_id":"CITY_STREET_RAIN_RIG","permit_status":"APPROVED"}
SC13 | camera | READY | TRUE |  |  | CAM001 available;CAM003 available | {"camera_setup_id":"CS04","cameras":["CAM001","CAM003"],"date":"2026-09-18"}
SC13 | stunt | READY | TRUE |  |  | medical_support_confirmed | {"stunt_id":"ST004","risk_level":"LOW"}
SC13 | cast | READY | TRUE |  |  | CAST001 available;CAST002 available | {"date":"2026-09-18"}

## production_state
scene_id | readiness_state | overall_status | last_update_ts | ready_to_shoot_flag | blocking_department
SC01 | READY | READY_TO_SHOOT | 2026-09-08 09:00 | TRUE
SC02 | READY | READY_TO_SHOOT | 2026-09-08 09:00 | TRUE
SC03 | BLOCKED | NEEDS_REPLAN | 2026-09-08 09:00 | FALSE | camera
SC04 | READY | READY_TO_SHOOT | 2026-09-08 09:00 | TRUE
SC05 | BLOCKED | NEEDS_REPLAN | 2026-09-08 09:00 | FALSE | cast
SC08 | BLOCKED | NEEDS_REPLAN | 2026-09-08 09:00 | FALSE | stunt
SC10 | BLOCKED | NEEDS_REPLAN | 2026-09-08 09:00 | FALSE | location
SC13 | BLOCKED | NEEDS_REPLAN | 2026-09-08 09:00 | FALSE | weather

## issues_log
issue_id | scene_id | type | severity | description | detected_by_agent | status
ISS001 | SC03 | CAMERA | MEDIUM | CAM002 in maintenance on 2026-09-13; no backup B-camera assigned. | camera | OPEN
ISS002 | SC05 | CAST | HIGH | Inspector Kumar (CAST006) unavailable on 2026-09-14. | cast | OPEN
ISS003 | SC08 | STUNT | HIGH | Set medic not yet assigned for HIGH risk warehouse fight stunt. | stunt | OPEN
ISS004 | SC10 | LOCATION | MEDIUM | Central Station location permit still PENDING. | location | OPEN
ISS005 | SC13 | WEATHER | HIGH | High chance of real rain overlapping with controlled rain rig. | weather | OPEN

## escalation_rules
rule_id | department | condition | escalation_target | rationale
R001 | location | status == 'BLOCKED' | Location Manager (CR005) -> Assistant Director | Permit issues need the location manager first; AD decides on replan if unresolved.
R002 | weather | status == 'BLOCKED' | Director of Photography (CR003) -> Assistant Director | DoP assesses whether coverage can be adapted before the AD replans the day.
R003 | camera | status == 'BLOCKED' | Director of Photography (CR003) | Equipment conflicts are resolved within the camera department where possible.
R004 | stunt | status == 'BLOCKED' | Stunt Coordinator (CR004) -> Assistant Director | Any unmet HIGH risk safety item blocks the AD from confirming the call sheet.
R005 | cast | status == 'BLOCKED' | Casting Director (CR006) -> Assistant Director | Cast conflicts need a recast or reschedule decision from the AD.